## WBS Dictionary
Work Package Name: Testing |  |  |  | WBS ID: 1.3.7
Description of Work: There will be accessibility testing for the website. There will be testing to make sure all transaction of website work correctly. There will be testing all the resource of MIS which will be available on the system.
Milestones: 1. Website feature testing complete 2. Integration testing complete 3. Resource accessibility testing complete |  |  |  | Due Date: 15/01/2023 15/02/2023 01/03/2023
ID | Activity | Resource | Labor |  |  | Material |  |  | Total cost
|  |  | Hours | Rate (USD) | Total | Unit | Cost | Total
1.3.7.1 | Website testing | PM | 5 | 10 | 50 |  |  |  | 50
1.3.7.2 | Hyperlink Testing | PM | 5 | 10 | 50 |  |  |  | 50
1.3.7.3 | MIS resource accessibility testing | PM | 50 | 10 | 500 |  |  |  | 500
1.3.7.4 | Integration testing | PM | 5 | 10 | 50 |  |  |  | 50
Quality Requirement: Website must be have registration form and can accessible for all MIS resource.
Acceptance Criteria: Website must be accessible for each registration user to take short taining course on MIS.
Technical Information: After training course, the certificate will be provided.
Contract Information: Testing will be conducted by the Project manager in charge of the area to be tested.

## Activity List
Activity | Activity Description | Immediate Predecessors | Estimate Duration
A | Finding MIS Resource | - | Update very time
B | Buy google's Domain | A | 1 week
C | Backend (database design) | B | 2 weeks
D | UI design | C | 4 weeks
E | Install atom and coding | D | 8 weeks
F | Set SEO | E,F | 4 weeks

## Activity Attribute
DC: C |  |  | Activity: Backend (database design)
Description of Work: The database design activity is an activity which has many process, it is included data flow design, UML design ,etc.
Predecessors | Relationship | Lead of Lag | Success or | Relationship | Lead or Lag
B | Start-to-Finish | Lead | D | Sart-to-Start | Lag
Number and Type of Resource require: 2 people |  | Skill Requirement: Coding, Business Analysis and System Analysis |  |  | Other Requirement resource: --
Type of Effort:
Location of Performance:
Imposed Dates or Other Constraints:
Assumption:

## Milestone List
Milestone List of Schol of Maths Project
Project: School of Maths Mobile App |  |  | Date: 15/11/2022
Milestone No. | Milestone | Mandatory/Optional | Completion Date | Verification
001 | Project start | Mandatory | 2022-11-15 | Client Approval
002 | Complete Gathering Requirements | Mandatory | 2022-12-15 | Client Approval
003 | Complete Design | Mandatory | 2023-01-15 | Client Approval
004 | Complete Coding | Mandatory | 2023-02-01 | Client Approval
005 | Complete Testing | Mandatory | 2023-02-15 | Client Approval
006 | Complete Implementation | Mandatory | 2023-03-01 | Client Approval
007 | Project End | Mandatory | 2022-03-15 | Client Approval

## Schedule Allocation
Task/month | 2022 |  | 2023
| Nov | Dec | Jan | Feb | Mar
INITIATION 1. Kick off meeting 2. Create Project charter
PLANNING 1. Identify, discuss, and prioritize risks 2. Create draft Gantt chart 3. Review and finalize Gantt chart 4. Prepare schedule and cost baseline 5. Prepare WBS 6. REQ Gathering 7. Create Prototype 8. Chreat SRS 9. Design UI 10. Design Database 11. Design Architecture
EXECUTING 1. Create Test case 2. Coding and Debug 3. User's manual 4. Create test plan 5. UAT Document 6. Installation 7. User Training
MONITORING AND CONTROLLING 1. Progress Meeting
PROJECT CLOSER 1. UAT 2. Closer Meeting

## Resource Requirement
WBS ID | Type of Resource | Quantity | Assumptions
1.1 Initiation
1.1.1 | Evaluation & Recommendations | 1 | People
1.1.2 | Develop Project Charter | 2 | People
1.1.3 | Devliverable: Submit Project Charter | 3 | People
1.1.4 | Project Sponsor Reviews Project Charter | 3 | People
1.1.5 | Project Charter Signed/Approved | 2 | People

## Resource BreakdownR
Project Name | School of Maths Mobile App | Date | 2022-11-15
Project Number | 01 | Document Number | 04
Project Manageer | Touch Sopheak | Project Owner/Client | Khy Srey Sros
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7
RBS Code/ID |  |  |  | Resource Categories and Types | Quantity | Notes
R1 |  |  |  | Project | 8
| R1.1 |  |  | Labor | 1
|  | R1.1.1 |  | Project Management | 2
|  |  | R1.1.1.1 | Project Manager | 1
|  |  | R1.1.1.2 | Assistant Project Manager | 1
|  | R1.1.2 |  | Software Develpment | 6
|  |  | R1.1.2.1 | Solutions Architect | 1
|  |  | R1.1.2.2 | Development Lead | 1
|  |  | R1.1.2.3 | Developer | 1
|  |  | R1.1.2.4 | Developer | 1
|  |  | R1.1.2.5 | Tester | 1
|  |  | R1.1.2.6 | Trainer | 1
| R1.2 |  |  | Equipment | 8
|  | R1.2.1 |  | Hardare | 2
|  |  | R1.2.1.1 | Laptop | 2
|  |  | R1.2.1.2 | Laptop | 2
|  |  | R1.2.1.3 | Projector | 1
|  |  | R1.2.1.4 | Printer | 1
|  | R1.2.2 |  | Software Develpment | 3
|  |  | R1.2.2.1 | Visio | 1
|  |  | R1.2.2.2 | Atom | 2
| R1.3 |  |  | Supplies | 5
|  |  | R1.3.1 | Ink | 1
|  |  | R1.3.2 | Paper | 1
|  |  | R1.3.3 | Binders | 3
| R1.4 |  |  | Locations
|  |  | R1.4.1 | School of Maths

## Activity Duration
Project Name | School of Maths Mobile App | Date | 2022-11-15
Project Number | 01 | Document Number | 05
Project Manageer | Touch Sopheak | Project Owner/Client | Khy Srey Sros
WBS ID# | Activity | Human Resources | Effort in Number of Hours | Duration Estimate | Lelvel of Confidence | Addtional Information
1.1.1 | Evaluation and Recommendations | 1 | 10 | 2 days | High
1.1.2 | Develop Project Charter | 1 | 10 | 2 days | Medium
1.1.3 | Deliverable: Submit Project Charter | 1 | 20 | 1 week | High
1.1.4 | Project Sponsor Reviews Project Charter | 1 | 10 | 2 days | High
1.1.5 | Project Charter Signed/Approved | 1 | 2 | 1 day | High

## Schedule
Activity Name | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023
2.0 Design phase
2.1 Preliminary Design
2.2 DB Design
2.3 Data Flow Design
Detail Design
Document Design
Activity Name | Nov 2022 | Dec 2022 | Jan 2023 | Feb 2023 | Mar 2023
2.0 Design phase
2.1 Preliminary Design
2.2 DB Design
2.3 Data Flow Design
Detail Design
Document Design
Duration of Normal Job Baseline Schedule Duration of Critical Job
Job | Activity Name | Dec Week1 | Dec Week2 | Dec Week3 | Dec Week4 | Jan Week1 | Jan Week2 | Jan Week3 | Jan Week4
1 | Approve plan
2 | Design Backend
3 | Data Flow Design
4 | Design the detail of Architecture
5 | Design Documentation
6 | User Interface Design
Duration of Normal Job Baseline Schedule Duration of Critical Job Milestone

## Activity cost estimate
Activity Cost Estimates
Project: Develop School of Math Mobile App | [7 empty] | Date: 15/11/2022
WBS No. | Resource | Direct Costs | Indirect Costs | Reserve | Estimate | Method | Assumptions/Constraits | Addtional Information | Range | Confidence Level
3.1.1 | 2 Developers for 50 hours | 50 hrs @10$ |  | 25$ | 500$ | Parametric | Must obtain functional manager approval to assign developer | N/A | xx-xx | 8
3.1.1 | Tester for 20 hours | 20 hrs @10$ |  | 10$ | 200$ | Parametric | Assume all functionality and transaction of website will be available to access, search and register to MIS course. | N/A | xx-xx | 7
3.1.1 | External Advisor |  | 12 hrs @10$ |  | 120$ | Parametric | The idea of design and promotion to everyone to get and easy to understand | N/A | xx-xx | 9

## Basis of Estimate
Basis of Estimate
Project: Develop School of Maths Mobile App | [5 empty] | Date: 15/11/2022
WBS Element: 1 Project Planning
Category | Material | Labor | Inirect Costs | Base Cost | Reserve | Total Cost | Funding Source | Cost Methodology
Planning | 300$ | 2500$ | 0 | 2000$ | 200$ | 5000$ | New Product Dev. | Parametric
WBS Description: Complete the development of School of Maths Mobile App
Cost Description: Labor is all inclusive of WBS element 1. Include 80 man hours of work performed at 10$ per hour. Managmement reserve of 10% has been identified based on a confidence level of 90%. Pricing was derived from existing hourly rates for one PMO employee and two Design Technology Group employees.
WBS Element: 1.1 Gather Requirements
Category | Material | Labor | Inirect Costs | Base Cost | Reserve | Total Cost | Funding Source | Cost Methodology
Planning
WBS Description: Gather requirements for School of Math Development App
Cost Description: Labor is all inclusive of WBS element 1.1. Includes 60 man hours of work performed at 10$ per hour. Management reserve of 10% has been identified based on a confidence level of 90%. Pricing was derived from existing hourly rate for one PMO employee and two Design Technology Group employees.

## Project Funding Requirment
Project Funding Requriement
Project: Develop School of Maths Mobile App |  |  |  |  | Date: 15/11/2022
Project phase | Funding type | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01
Initiation | Manpower | 500
Initiation | Equipment/Capital | 200
Planing | Manpower |  | 500
Planing | Equipment/Capital |  | 200
Design | Manpower |  |  | 600
Design | Equipment/Capital |  |  | 400
Prototype Build | Manpower |  |  |  | 700
Prototype Build | Equipment/Capital |  |  |  | 450
Testing | Manpower |  |  |  | 500
Testing | Equipment/Capital |  |  |  | 200
Transition to operations | Manpower |  |  |  |  | 100
Transition to operations | Equipment/Capital |  |  |  |  | 300
Project closeout | Manpower |  |  |  |  | 350
Project closeout | Equipment/Capital
Totals |  | 700 | 700 | 1000 | 1850 | 750